## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Research | 0.5 | 2022-01-13 | Preliminary research on maze creating algorithms
Basic classes & data structures | 2.5 | 2022-01-14 | Created the classes to support the maze creation algorithm. Started work on the maze creation.
Recursive algorithm finish + visualizaition | 4.5 | 2022-01-01 | Finished implementation, and then created the visualization algorithm. The algorythm suffers from stack overflowing and poor performance for large grids for now. Then connected the two together and have a visualization algorithm.
Algorithm animation | 1 | 2022-01-18 | I had to do some reading to remind myself how to have the maze updated in real time. Fortunately it didn't take me too long to accomplish that
Iterative algorithm implementation + started work on GUI | 2 | 2022-01-18 | To counteract the fact that my recursive algorythm dies at 150x150 cells, I implemented an iterative algorythm using a stack. For now it offers worse performance but it will theoretically finish execution. Wohoo. Started working on GUI but ran into an issue that I couldn't press my button. That was rather embarassing but it turns out I was missing the Event Handler. Did a simple button graphics and imported the [original] background from my other Unity project.
GUI completion | 1.5 | 18-19.01.2022 | After resolving that issue after a break, I was able to complete GUI in no time. The structure of my code allowed me to quickly attach the UI components to the rest of the code and therefore user stories 2 & 3 are now complete. User story 4 should be as well, but I'll continue working on it later in the day. Getting to this point took me 12 hours - I am comfortable I'll be able to polish this and add some additional features even in the remaining 8 hours.
Optimizations of the visual generation & Iterative algorithm optimization attempt | 2 | 2022-01-20 | I've started getting sick on mid 18th (covid as I learned a day later) so I unfortunately wasn't able to finish it then. Having become fine on the 20th, I went back to optimizing the visualizaiton algorythm by setting all the pixels at once. It turned out to be a good call. I ran into some issues with optimizing the iterative algorithm (please see code comments), and in the end I updated to Unity 2021 from 2018. I am aware that the requirements were that I was to do it in 2020 or later, but I decided to leave that [foolishly] for later. That didn't help me with my iterative improvements - however, it significantly boosted performance of the visualization algorithm and made the recursive algorithm not overflow anymore. I don't know why, but I suspect something in 2018's version was throttling the execution via running default threads which werent necessary for my application. Just a guess.
Work on testing user story 4. | 0.5 | 2022-01-20 | No problems here, I have previously properly set up constraints so different resolution weren't problematic.
Changeable animation speed + Vertical bias | 0.5 | 2022-01-20 | Some additional features for fun. | X
Save picture to PNG (for printing!) | 0.5 | 2022-01-20 | Saves to the same directory where the game executable is. | X
Minor bug fixing, finishing up, generating executable file and making sure everything is fine | 1 | 2022-01-20 | Removal of some minor bugs, improving the scale of the mazes for super small/super big mazes.
Final comments | 0 | 2022-01-20 | It was a very fun and challenging assessment. I've been leading documentation in github & code mostly so I apologize if this spreadsheet is not descriptive enough. I've attached my commit history too so that you can take a look at what I was doing when I was noting stuff on the fly. Now that I look at it, Row 8 is kind of a bonus since the recursive implementation is my main solution, but at that moment I was planning for that one to be the intended solution.
Creating UML diagram | 0.75 | 2022-01-20 | I'm not that big of a fan of making UML diagrams, hopefully this one isn't too bad. I was using my other University project as reference. | X
Total amount of hours | 15,5 | I took the liberty of doing this manually as my excel was going crazy.